## FY2012
Medicaid/MCHP Cost Containment Initiatives, FY 2012
Report 1 due May 31
Report 2 due July 31
Report 3 due September 30
|  | FY2012 Impact (General Funds) |  | Assumed | Actual
# | Initiative | Budget Estimate | Current Estimate | Implementation Date | Implementation Date | Responsible | Notes/Updates
Prior Initiatives
1 | Capitation for Medicare Advantage | budget-neutral |  | FY 2010 |  | Joel | Payment of capitation rates to Medicare Advantage plans ended at the end of Calendar Year 2010. Two plans had been receiving capitation payments, but elected to terminate their capitation agreements with the Department because they deemed the capitation rates offered by the Department to be insufficient.
2 | Substance abuse expansion | budget-neutral (use ADAA funds only) |  | FY 2010 | FY 2010 | Planning/OHS | $8M transfered from ADAA, however expenditures are significantly higher
3 | Pay providers lower of Medicaid or Medicare rates (for duals) | -22200000 | 13000000 | FY 2011 | 2010-08-01 | Operations | Implemented for Dates of Service beginning August 1. 2010
4 | MHIP Waiver | -5000000 |  | FY 2011 |  | Planning | CMS is currently reviewing proposal. A decision is expected by June 30, because the next HealthChoice renewal period begins July 1.
5 | Collect rebates on MCO-paid pharmaceuticals ($11m GF collections less $8m GF clawback) | -3000000 |  | FY 2011 |  | Pharmacy | Invoices to Drug Manufacturers for MCO claims during CY 2010 (Mar 23rd - Dec 31st) were sent in February 2011. However, until we receive the appropriate unit rebate data from CMS we can not perform a reconciliation to determine the actual budget impact. Collected $24M GF YTD
6 | Suspend Medicaid payments for incarcerated individuals | -2500000 |  | FY 2011 | TBD | Operations/OES | Completed matching program in Jan 2011 identifying approximately 900 clients that need to be researched by OES for possible manual disenrollment. Based on research, finalize business rules and develop automated process to disenroll incarcerated clients from MCOs.
7 | Funding to reduce SSI/LIS backlogs | FY 2011 only |  | FY 2011 | Feb. 2011 | OES | Project began Feb. 2011, anticipated completion date is August 2011.
8 | MMIS replacement (w/90% FF) | $1,640,855 (in DoIT budget) |  | FY 2011 |  | Operations | Procurement in BAFO stage. Budget is appropriate for FY12.
DHMH proposals
9 | Seek CHIPRA enrollment bonus | -10549086 |  | December award |  | Planning | Application materials are due this fall to CMS.
10 | Require DC hospitals to accept FFS rates | -5700000 | 5700000 | July |  | Finance/OHS | Reviewing data received to evaluate how to implement.
11 | Strict review of emergency coverage | -5000000 | 5000000 | August | 2011-07-01 | Mary M | Regs in signoff process
12 | Evidence-based pharmacy coverage decisions | -1000000 |  | August |  | MaryM/Pharmacy | In contract discusions with UMD for peer to peer phone consults
13 | TPL initiative - End-Stage Renal Disease | -1000000 |  | July | 2011-05-01 | OES | 541 Recipient letters were mailed in May advising recipients that they must provide proof that they have applied for all benefits for which they may be eligible. We anticipate on completing the project within 6 months
14 | Deny off-label uses of antipsychotics | -800000 |  | October |  | Pharmacy | Original Initiative was for 7 PINs and total project cost of $900K. Final budget item is for 1 PIN and $245K for outsourcing/contracting. Currently working with MHA to develop project plan and protocols necessary to implement, including the vendor that we would contract with to provide services. Project will be implemented in phases. Expected start date Oct 2011. Actual budget impact undetermined at this time
15 | Reduce Maximum Allowable Cost for generics | -500000 |  | July |  | Pharmacy | On target
16 | Electronic Health Records / e-Prescribe (w/90% FF) | 500000 |  | TBD |  | Operations | CSC contract amendment to BPW on 6/1 to provide system support for incentive payments. Draft SMHP and APD in process for submission to CMS. Will require ASO contract to administer and audit provider applications for reimbursement.
17 | Patient-Centered Medical Home | 750000 |  | July |  | Planning | Medicaid is working with MHCC. 54 practices have been selected and payments are expected to begin July.
Other proposals in allowance
18 | Use patient resources for Medicare premiums in lieu of State funds | -3500000 |  | July | Unable to implement | OES | Unable to implement project. MMIS & CARES currently has hard system coding which will not permit us to implement project. Also see #27.
19 | Tighten MCO efficiency adjustment | -2750000 | 9000000 | January | 2012-01-01 | Finance | On target
20 | Continue rate freeze to non-HSCRC hospitals (e.g. CNMC/KKI) | -1500000 | 542000 | July | 2011-07-01 | Finance | On target, Provider has to be notified
21 | TPL initiative - Veterans/Other | -1000000 |  | TBD | TBD | Operations | Unknown. Need more information regarding PARIS matches and impact on eligibility to determine processes to implement and impact. In planning stage
22 | 1% reduction to Waiver providers (exc. Case Management) | -1000000 |  | July | 2011-07-01 | OHS | Regs on target for July implementation
23 | 1% reduction to Private Duty Nursing | -500000 |  | July | 2011-07-01 | OHS | Regs on target for July implementation
24 | 1% reduction to physician rates (FFS) | -500000 |  | July | 2011-07-01 | OHS | Regs on target for July implementation
25 | Continue rate freeze to Home Health providers | -30000 |  | 2012-01-01 | 2012-01-01 | OHS | Will provide feedback at next deliverable.
26 | Implement Community First Choice | budget-neutral |  | TBD |  | Planning/OHS | Will provide feedback at next deliverable.
27 | Adjust patient resources to cover Medicare premiums | 75000 |  | July | Unable to implement | OES | Unable to implement project. MMIS & CARES currently has hard system coding which will not permit us to implement project. Also see # 18.
28 | 4% AERS rate increase for STEPS | 130000 |  | July | 2011-07-01 | OHS | On target
29 | Eligibility Systems (w/90% FF) | 900000 |  | TBD |  | Operations/OES | Innovator Grant approved by CCIIO
Supplemental Budget items
30 | Investigate SSNs in enrollment data | 20000 |  | TBD | 2011-05-01 | OES | The DREP unit has begun the CARES/MMIS SSN # clean-up, reconciliation and validation project. Project timeline is estimated for 9 months.
31 | Complete/oversee new DHR MoU | 90000 |  | TBD | TBD | OES | MOU is in the final stages of review, anticipate signed document before 9-1-2011
32 | Provider re-enrollment | 225000 |  | TBD | TBD | OHS | Procuring a vendor
Effect of legislative action
33 | Contractor-identified initiatives ($15m allowance + $5m leg cut) | -20000000 |  | TBD | Not expected for 2011 | OES/OHS/Finance/Operations | Currently determining which initiatives will provide the best return on investment. Will provide feedback at next deliverable.
34 | 2% reduction to CY2011 MCO rates ($8.2m allowance + $9.5m leg cut includes physician rate reductions) | -17700000 |  | May-December |  | Finance | A rate reduction was made for May ($19M). In addition a physician fee decrease of $ 5.5M will be implemented for July 1, 2011 rates of which $500k will be in the PAC program.
35 | Reduce non-emergency transportation costs | -1087500 |  | TBD | 2012-01-01 | OHS
36 | Reduce pharmacy dispensing fees | -275000 |  | July |  | Pharmacy | On target
37 | Family Planning Program expansion | budget neutral (use FHA funds only) |  | January | January | OHS | On target