## RFP Timeline
MARYLAND DEPARTMENT OF HEALTH
OFFICE OF PROCUREMENT AND SUPPORT SERVICES
PRELIMINARY RFP TIMELINE
STEP | DAYS | DATE
Require Decision to Program | 340 | 2017-01-05
CFT | 50 | 2017-12-11
PRG | 30 | 2018-01-29
DBM/DoIT REVIEW | 40 | 2018-02-28
eMM POSTING | 14 | 2018-04-09
PRE-PROPOSAL DATE | 14 | 2018-04-23
Q & A CUT OFF | 7 | 2018-05-07
PROPOSALS DUE (35 days minimum after posting to eMM) | 35 | 2018-05-14
MBE INFORMATION CHECKED | 5 | 2018-06-18
EVALUATION COMMITTEE ORIENTATION | 5 | 2018-06-21
EVALUATION COMMITTEE MEETING FOR TECHNICALS | 28 | 2018-06-26
CLARIFICATION/DISCUSSION MEETING (Demonstrations if Required) | 28 | 2018-07-24
EVALUATION COMMITTEE MEETING FOR FINANCIAL | 7 | 2018-08-21
EVALUATON COMMITTEE MEETING TO RANK BOTH TECHNICAL AND FINANCIAL PROPOSALS | 7 | 2018-08-28
BAFO LETTERS | 10 | 2018-09-04
RECOMMENDATION LETTER FORWARDED TO OPASS | 10 | 2018-09-14
LETTERS TO VENDORS - RECOMMENDED VENDOR AND LOSING VENDORS | 14 | 2018-09-24
CONTRACT REVIEW (to ensure all information is received and vetted) | 21 | 2018-10-08
ENTER CONTRACT INFORMATION INTO ADPICS | 7 | 2018-10-29
SUBMIT CONTRACT FOR LEGAL APPROVAL | 2 | 2018-11-05
SUBMIT BPW ACTION AGENDA (along with misc paperwork) all two board meetings | 35 | 2018-11-06
FINALIZE INFORMATION IN ADPICS | 7 | 2018-12-11
FORWARD CONTRACT TO APPROPRIATE DEPUTY SECRETARY FOR APPROVAL | 7 | 2018-12-18
FORWARD SIGNED CONTRACTS TO PROGRAM | 7 | 2018-12-25
CONTRACT START DATE | 14 | 2019-01-01
* Populate Row 25, Column 'C' using numerical format (e.g., 1/1/19) to calculate start date for drafting the documents.
Formulas:
DATE = IF(WEEKDAY([DATE, row below]-[DAYS],1)=7,[DATE, row below]-[DAYS]+2,+IF(WEEKDAY([DATE, row below]-[DAYS],1)=1,[DATE, row below]-[DAYS]+1,[DATE, row below]-[DAYS]+0))