## STEPS
24 STEPS FOR PROCUREMENTS SUBJECT TO DBM APPROVAL
(FROM WHEN AN AGENCY DECIDES TO DO A PROCUREMENT TO WHEN THE CONTRACTOR COMMENCES WORK)
PLANNING (4 steps)
1 | Identify what you want to procure.
2 | Prepare specifications and determine the means for advertising and distributing the solicitation.
3 | Obtain internal agency approvals.
4 | Obtain approval of specifications from DBM.
PROCURING (18 steps)
5 | Advertise (post) the availability of the solicitation in eMarylandMarketPlace and elsewhere.
6 | Distribute the solicitation or make it available (e.g. on the agency web site), to vendors that cannot get the solicitation via the advertising venues.
7 | Hold a Pre-Bid/Proposal Conference.
8 | Prepare and distribute Minutes or a Summary of the conference to ALL known potential bidders/offerors.
9 | Solicitation questions are received and answered, with answers to substantive questions being distributed to ALL known potential bidders/offerors.
10 | Any changes to the solicitation are prepared in an addendum and distributed to ALL known potential bidders/offerors.
11 | The Procurement Officer receives bids/proposals.
12 | Bids/proposals are opened. *
| » | Bids are opened publicly and a record is prepared of the bid opening (a bid abstract).
| » | Proposals are opened in the presence of at least 2 State employees, not publicly, and a record is prepared of the proposals received (a register of proposals) and of the opening.
13 | Bids/proposals are checked for compliance with various requirements, checking first the completion of MBE forms.
14 | A decision is made of whether any deficiency is waivable, versus curable, versus fatal. *
15 | Vendors are notified of curable deficiencies. **
16 | Required additional information or documents are received and evaluated. **
17 | An award decision is made. **
18 | Required additional MBE forms are obtained, if necessary, and the contractor signs the contract. **
19 | Final internal agency approvals are obtained.
20 | The award is submitted for DBM and, if necessary, BPW approval.
21 | The contract is signed by the agency and transmitted to the Contractor.
22 | Excess bids/proposals are destroyed and the procurement file is completed.
PERFORMING (2 steps)
23 | Work initiation conference is held.
24 | Contractor commences work.
* Steps are the same for CSB and CSP with minor variances.
** Steps have variances between CSB and CSP, and CSP has additional steps added in between these steps.
CSP -
Steps 1-14 are the same as CSB.
15 | The evaluation committee members individually read the technical proposals
16 | The evaluation committee meets to discuss the proposals, including strengths and weaknesses, ambiguities, and omissions
17 | “Cure letters” are issued to obtain:
—Omitted items or information
—But, missing/incomplete MBE forms generally are not curable
—Written clarifications of ambiguous material
—Written explanations or justifications for any information that is not sufficiently supported
(Vendors are notified of curable deficiencies - Issues of responsibility for sealed bid procurements, #15)
18 | The evaluation committee prepares generic and specific questions to ask offerors at the oral presentations, including any lingering or new questions based upon the cure letter responses
(Required additional information or documents is received and evaluated, #16)
19 | Oral presentations are held with offerors
20 | Offerors submit additional information, clarifications or changes based upon the oral presentations
21 | The evaluation committee makes final technically qualified determinations for proposals and ranks the remaining technically qualified proposals based upon the evaluation criteria in the RFP
22 | Financial proposals are opened and reviewed for offerors with technically qualified proposals
23 | If necessary, discussions are held concerning the financial proposals
24 | Best and Final Offers (BAFO) are invited, received and evaluated
25 | Based upon the combined technical and financial rankings the evaluation committee recommends an offeror to receive the contract award
26 | The procurement officer and agency head accept the recommendation of the evaluation committee or select a different offeror for the award
(An award decision is made, #17)
27 | The contractor signs the contract and provides all required post award items, such as:
—2 additional MBE forms, or waiver justification
—Bonds
—Insurance
—Contract and Conflict-of-Interest Affidavits
(Required additional MBE forms are obtained and the contractor signs the contract, #18)
28 | Non-winning offerors are notified of their status and provided all permissible information
29 | Debriefings are held
Picks up with #19 from CSB and is the same until the end for a total of 35 Steps for CSPs.

## TIME FRAMES
24 STEPS FOR PROCUREMENTS SUBJECT TO DBM APPROVAL |  |  | PROCUREMENT STEPS AND MINIMUM TIME FRAMES FOR COMPLETION | [8 empty] | PROCUREMENT STEPS AND MINIMUM TIME FRAMES FOR COMPLETION
(FROM WHEN AN AGENCY DECIDES TO DO A PROCUREMENT TO WHEN THE CONTRACTOR COMMENCES WORK) |  |  | (Except for the first 3 STEPS) | [8 empty] | (Except for the first 3 STEPS)
| PLANNING (4 steps) |  | Competitve Sealed Bidding | No DBM Approval with No MBE goal | No DBM Approval with MBE goal | No DBM Approval with No MBE goal | No DBM Approval with MBE goal | DBM Approval with No MBE goal | DBM Approval with MBE goal | DBM Approval with No MBE goal | DBM Approval with MBE goal | Competitve Sealed Proposals | No DBM Approval with No MBE goal | No DBM Approval with MBE goal | No DBM Approval with No MBE goal | No DBM Approval with MBE goal | DBM Approval with No MBE goal | DBM Approval with MBE goal | DBM Approval with No MBE goal | DBM Approval with MBE goal
1 | Identify what you want to procure. |  |  | <$200,001 | <$200,001 | >$200,000 | >$200,000 | <$200,001 | <$200,001 | >$200,000 | >$200,000 |  | <$200,001 | <$200,001 | >$200,000 | >$200,000 | <$200,001 | <$200,001 | >$200,000 | >$200,000
2 | Prepare specifications and determine the means for advertising and distributing the solicitation.
3 | Obtain internal agency approvals.
4 | Obtain approval of specifications from DBM.
|  |  | (DBM Approval) |  |  |  |  | 28-35 days | 28-35 days | 28-35 days | 28-35 days | (DBM Approval) |  |  |  |  | 28-35 days | 28-35 days | 28-45 days | 28-45 days
PROCURING (18 steps)
5 | Advertise (post) the availability of the solicitation in eMarylandMarketPlace and elsewhere. |  | (Advertise & Receive Bids) | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | 21-30 days for simple; 30-40 days difficult | (Advertise & Receive Proposals) | 30-40 days | 30-40 days | 30-60 days | 30-60 days | 30-40 days | 30-40 days | 30-60 days | 30-60 days
6 | Distribute the solicitation or make it available (e.g. on the agency web site), to vendors that cannot get the solicitation via the advertising venues.
7 | Hold a Pre-Bid/Proposal Conference.
8 | Prepare and distribute Minutes or a Summary of the conference to ALL known potential bidders/offerors.
9 | Solicitation questions are received and answered, with answers to substantive questions being distributed to ALL known potential bidders/offerors.
10 | Any changes to the solicitation are prepared in an addendum and distributed to ALL known potential bidders/offerors. |  | (Determine Responsiveness) | 0 days | 0 days | 0 days | 0 days | 0 days | 0 days | 0 days | 0 days | (Determine if Proposals | 34-65 days | 34-65 days | 34-65 days | 34-65 days | 34-65 days | 34-65 days | 34-65 days | 34-65 days
11 | The Procurement Officer receives bids/proposals. | [10 empty] | are Reasonably Susceptible of
12 | Bids/proposals are opened. * | [10 empty] | Receiving an Award) *
| » | Bids are opened publicly and a record is prepared of the bid opening (a bid abstract). | (Determine Responsibility) | 0-5 days | 0-5 days | 0-5 days | 0-5 days | 0-5 days | 0-5 days | 0-5 days | 0-5 days | (Notification & Debriefings) | 7-14 days | 7-14 days | 7-14 days | 7-14 days | 7-14 days | 7-14 days | 7-14 days | 7-14 days
| » | Proposals are opened in the presence of at least 2 State employees, not publicly, and a record is prepared of the proposals received (a register of proposals) and of the opening.
13 | Bids/proposals are checked for compliance with various requirements, checking first the completion of MBE forms. |  | (Notice of Award) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE) | (Notice of Award) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE) | 1-5 days | (part of MBE)
14 | A decision is made of whether any deficiency is waivable, versus curable, versus fatal. * |  | (Receive final MBE forms) |  | 14 days (10 working days) |  | 14 days (10 working days) |  | 14 days (10 working days) |  | 14 days (10 working days) | (Receive final MBE forms) |  | 14 days (10 working days) |  | 14 days (10 working days) |  | 14 days (10 working days) |  | 14 days (10 working days)
15 | Vendors are notified of curable deficiencies. ** |  | (Outside Agency Approvals) |  |  | 28 days - BPW * | 28 days - BPW * | 7-10 days - DBM | 7-10 days - DBM | 44 days | 44 days | (Outside Agency Approvals) |  |  | 28 days - BPW ** | 28 days - BPW ** | 7-10 days - DBM | 7-10 days - DBM | 44 days | 44 days
16 | Required additional information or documents are received and evaluated. ** |  | (Execute signed Contract) | 1-3 days | 1-3 days | 1-3 days | 1-3 days | 1-3 days | 1-3 days | 1-3 days | 1-3 days | (Execute signed Contract) | 1-5 days | 1-5 days | 1-5 days | 1-5 days | 1-5 days | 1-5 days | 1-5 days | 1-5 days
17 | An award decision is made. **
18 | Required additional MBE forms are obtained, if necessary, and the contractor signs the contract. ** |  | SUBTOTAL to CONTRACT AWARD | 23-53 days | 36-62 days | 51-81 days | 64-90 days | 58-98 days | 71-107 days | 95-132 days | 108-141 days | SUBTOTAL to CONTRACT AWARD | 73-129 days | 86-138 days | 101-177 days | 114-186 days | 108-174 days | 121-183 days | 145-238 days | 158-247 days
19 | Final internal agency approvals are obtained. |  | (Core Procurement Phase) | [8 empty] | (Core Procurement Phase)
20 | The award is submitted for DBM and, if necessary, BPW approval.
21 | The contract is signed by the agency and transmitted to the Contractor. |  | COMMENCEMENT of CONTRACT/ DELIVERY DATE | 1-7 days | 1-7 days | 7-14 days | 7-14 days | 1-7 days | 1-7 days | 7-14 days | 7-14 days | COMMENCEMENT of CONTRACT | 7-14 days | 7-14 days | 14-30 days | 14-30 days | 7-14 days | 7-14 days | 14-30 days | 14-30 days
22 | Excess bids/proposals are destroyed and the procurement file is completed.
| PERFORMING (2 steps) |  | TOTAL | 24-60 days | 37-69 days | 58-95 days | 71-104 days | 59-105 days | 72-114 days | 102-146 days | 115-155 days | TOTAL | 80-143 days | 93-152 days | 115-207 days | 128-216 days | 115-188 days | 128-197 days | 159-258 days | 172-277 days
23 | Work initiation conference is held.
24 | Contractor commences work. |  | * Only includes lead time for formal item submission to the BPW. Does not include any time for internal agency approvals. | [8 empty] | * Cumulative timeframe for 6 STEPS.
| * Steps are the same for CSB and CSP with minor variances. | [10 empty] | ** Only includes lead time for formal item submission to the BPW. Does not include any time for internal agency approvals.
** Steps have variances between CSB and CSP, and CSP has additional steps added in between these steps.
CSP -
Steps 1-14 are the same as CSB.
15 | The evaluation committee members individually read the technical proposals
16 | The evaluation committee meets to discuss the proposals, including strengths and weaknesses, ambiguities, and omissions
17 | “Cure letters” are issued to obtain:
—Omitted items or information
—But, missing/incomplete MBE forms generally are not curable
—Written clarifications of ambiguous material
—Written explanations or justifications for any information that is not sufficiently supported
(Vendors are notified of curable deficiencies - Issues of responsibility for sealed bid procurements, #15)
18 | The evaluation committee prepares generic and specific questions to ask offerors at the oral presentations, including any lingering or new questions based upon the cure letter responses
(Required additional information or documents is received and evaluated, #16)
19 | Oral presentations are held with offerors
20 | Offerors submit additional information, clarifications or changes based upon the oral presentations
21 | The evaluation committee makes final technically qualified determinations for proposals and ranks the remaining technically qualified proposals based upon the evaluation criteria in the RFP
22 | Financial proposals are opened and reviewed for offerors with technically qualified proposals
23 | If necessary, discussions are held concerning the financial proposals
24 | Best and Final Offers (BAFO) are invited, received and evaluated
25 | Based upon the combined technical and financial rankings the evaluation committee recommends an offeror to receive the contract award
26 | The procurement officer and agency head accept the recommendation of the evaluation committee or select a different offeror for the award
(An award decision is made, #17)
27 | The contractor signs the contract and provides all required post award items, such as:
—2 additional MBE forms, or waiver justification
—Bonds
—Insurance
—Contract and Conflict-of-Interest Affidavits
(Required additional MBE forms are obtained and the contractor signs the contract, #18)
28 | Non-winning offerors are notified of their status and provided all permissible information
29 | Debriefings are held
Picks up with #19 from CSB and is the same until the end for a total of 35 Steps for CSPs.